# Narrative Justification — Community Reading and Food Support Pilot

## Overview

This narrative summarizes progress against KPIs for the reporting period **2026-04-01 to 2026-06-30**.

## Results against KPIs

### 1. Youth reading workshops delivered

Target: 8; Actual: 9

Measurement: Workshop sessions delivered

Evidence summary: Evidence found in attendance_register.csv, field_visit_notes.txt, kpi_progress.csv supporting measurement: Workshop sessions delivered.

Key sources: attendance_register.csv, field_visit_notes.txt, kpi_progress.csv

### 2. Learners reached

Target: 120; Actual: 137

Measurement: Unique learners attending

Evidence summary: Evidence found in field_visit_notes.txt, kpi_progress.csv, receipts_summary.csv supporting measurement: Unique learners attending.

Key sources: field_visit_notes.txt, kpi_progress.csv, receipts_summary.csv

### 3. Food parcels distributed

Target: 200; Actual: 214

Measurement: Parcels issued to households

Evidence summary: Evidence found in field_visit_notes.txt, kpi_progress.csv, photo_log.txt supporting measurement: Parcels issued to households.

Key sources: field_visit_notes.txt, kpi_progress.csv, photo_log.txt

### 4. Receipts reconciled

Target: 95%; Actual: 98%

Measurement: Eligible spend linked to receipt records

Evidence summary: Evidence found in field_visit_notes.txt, kpi_progress.csv, receipts_summary.csv supporting measurement: Eligible spend linked to receipt records.

Key sources: field_visit_notes.txt, kpi_progress.csv, receipts_summary.csv

## Data integrity & audit trail

All referenced sources are copied into `03_SOURCES/` with filenames preserved. The evidence table links each KPI to source filenames.

## Risks / flags

Known gap: Two photo consent forms pending; learner images excluded from public appendix.

Known gap: Finance officer should confirm receipt total before final donor submission.