# Executive Summary — Evidence Pack

**Organization:** BrightStart Community Trust

**Donor/Funder:** Ubuntu Community Fund

**Project:** Community Reading and Food Support Pilot

**Grant ID:** GOLDEN-evidex-488c40b13ce3498ed076

**Reporting Period:** 2026-04-01 to 2026-06-30

## 1) Purpose

This evidence pack was prepared to support **Donor evidence pack for community reading and food support pilot** under time pressure. It consolidates KPI evidence, sources, and narrative justifications into an audit-ready structure.

## 2) Coverage

KPIs included: 4

Source files reviewed: 5

Appendix summaries: Included

## 3) KPI snapshot

Youth reading workshops delivered — Target: 8, Actual: 9 (Workshop sessions delivered)

Learners reached — Target: 120, Actual: 137 (Unique learners attending)

Food parcels distributed — Target: 200, Actual: 214 (Parcels issued to households)

Receipts reconciled — Target: 95%, Actual: 98% (Eligible spend linked to receipt records)

## 4) Notes / constraints

Known gaps:

Two photo consent forms pending; learner images excluded from public appendix.

Finance officer should confirm receipt total before final donor submission.

Avoided claims:

Do not claim audited financial assurance.

Do not claim public permission to use learner images.

Do not imply donor approval has already been granted.